## quarterly Progress report
Name of PIA | Organisation for Rural Reconstruction & Integrated Social Service Activities (ORRISSA)
Registration No. of PIA | 1838-102/1988-89
Project Title | Strengthening adivasi farm women self help cooperatives to enable them pursue sustainable livelihoods.
Date of PAC approval
Date of Fund release | 25.10.2013
Reporting Period | 01.01.2014 to 31.03.2014 | [10 empty] | From
| Parameters | UoM(Unit of measurement)examples given | Cumulative Target upto the end of previous quarter since inception of project (A') | Progress upto previous reporting period (Up to end of previous quarter since inception of project) (A) | % target achievement till the previous quarter end, since inception | Target for the current quarter (B') | Current Period ( progress for the reporting or current quarter) (B) | % target achievement in the current quarter | Cumulative target till the end of reporting/currently ended quarter (A'+B') | Progress Up to end of reporting period ( cumulative till the end of reporting/ currently ended quarter) (A)+(B) | % achievement of the target [(A+B/A'+B')*100]
1.Outreach
1.1 | No. of Mahila Kisan covered (Castewise): Please give total no. here and the break up below | No. |  |  |  | 2200 | 2172 | 98.7273 | 2200 | 2172 | 98.7273
1.1.1 | ST |  |  |  |  | 1800 | 1855 | 103.0556 | 1800 | 1855 | 103.0556
1.1.2 | SC |  |  |  |  | 300 | 206 | 68.6667 | 300 | 206 | 68.6667
1.1.3 | OBC |  |  |  |  | 100 | 111 | 111 | 100 | 111 | 111
1.1.4 | Others | [6 empty] | #DIV/0! | 0 | 0 | #DIV/0!
1.2 | No. of women farmers trained on atleast one activity covered under MKSP(Castewise): Please Provide total no. and breakup as mentioned below | No. | 80 | 67 | 83.75 | 100 | 60 | 60 | 180 | 127 | 70.5556
1.2.1 | ST |  |  | 65 | #DIV/0! | 80 | 38 | 47.5 | 80 | 103 | 128.75
1.2.2 | SC |  |  |  | #DIV/0! | 15 | 14 | 93.3333 | 15 | 14 | 93.3333
1.2.3 | OBCs |  |  | 2 | #DIV/0! | 5 | 8 | 160 | 5 | 10 | 200
1.2.4 | Minorities |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
1.3 | No. of women farmers within SHGs trained in at least one of the activities covered. Give Total No. (Provide Breakup in the annexure) | No. | 80 | 67 | 83.75 | 100 | 60 | 60 | 180 | 127 | 70.5556
1.3.1 | Sustainable Agriculture |  | 80 | 67 | 83.75 | 100 | 60 | 60 | 180 | 127 | 70.5556
1.3.2 | NTFP activity |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
1.3.3 | Livestock activity |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
1.4 | Interventions at the level of Community Institutions (Please provide data in the manner mentioned below) |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
1.4.4 | No. of SHGs covered |  | 90 | 64 | 71.1111 | 80 | 95 | 118.75 | 170 | 159 | 93.5294
1.4.5 | No. of Village level Federations covered |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
1.4.6 | No. of Cluster Level/Block level Federations covered |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
1.4.7 | % of the SHGs intervened covered | % |  |  | #DIV/0! |  | #REF! | #REF! | 0 | #REF! | #REF!
[9 empty] | 0 | 0
1.5 | Livelihood groups: Please give the total no. of Livelihood groups formed and the breakup in the manner mentioned below | No. |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
1.5.1 | Number of village level Producers'/Collectors' Groups formed |  | 60 | 58 | 96.6667 | 11 | 10 | 90.9091 | 71 | 68 | 95.7746
1.5.3 | Number of Producer Organisations registered (Give the details with Year of Registration in annexure) |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
1.5.4 | Number of SHG members who are part of Producer's/Collector's groups (Please don't double count members) |  | 900 | 960 | 106.6667 | 1000 | 945 | 94.5 | 1900 | 1905 | 100.2632
[9 empty] | 0 | 0
1.5 | Geographical coverage: Please provide the details in the manner mentioned below | No. | [5 empty] | #DIV/0! | 0 | 0 | #DIV/0!
1.5.1 | Revenue Villages |  |  |  | #DIV/0! | 19 | 19 | 100 | 19 | 19 | 100
1.5.2 | No. of Gram Panchayats |  |  |  | #DIV/0! | 5 | 5 | 100 | 5 | 5 | 100
1.5.3 | Number of Blocks |  |  |  | #DIV/0! | 2 | 2 | 100 | 2 | 2 | 100
1.5.4 | Number of Districts |  |  |  | #DIV/0! | 2 | 2 | 100 | 2 | 2 | 100
[9 empty] | 0 | 0
1.6 | Total Agricultural area of Women Farmers in the area of operations (Net cropped area): Please give the total area and the breakup as mentioned below | acre |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
1.6.1 | Net cropped area in acres under Sustainable Agriculture of MKSP owned by Mahila Kisan |  |  |  | #DIV/0! | 2000 | 2460.98 | 123.049 | 2000 | 2460.98 | 123.049
1.6.2 | Total agricultural land under Share cropping / lease by the Women Farmers covered under MKSP |  |  |  | #DIV/0! | 200 | 57.26 | 28.63 | 200 | 57.26 | 28.63
1.6.3 | Total irrigated area out of the total agricultural area of Women Farmers in the area of operations of PIA under MKSP |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
[9 empty] | 0 | 0
2. Input: | [8 empty] | 0 | 0
2.1 | Capacity building: Please provide the informations in the manner mentioned below | [7 empty] | 0 | 0
2.1.1 | No. of training modules developed for Mahila Kisan | No. | 1 | 1 | 100 | 2 | 2 | 100 | 3 | 3 | 100
2.1.2 | No. of Training modules developed for Community Resource Persons | No. | 1 | 1 | 100 | 1 | 1 | 100 | 2 | 2 | 100
2.1.3 | No. of training modules developed for Community Para Professionals | No. | 1 | 1 | 100 | 1 | 1 | 100 | 2 | 2 | 100
2.1.4 | No. of days of Capacity building of Mahila Kisan | No. | 8 | 8 | 100 | 10 | 4 | 40 | 18 | 12 | 66.6667
2.1.5 | No. of days of Capacity building of Community Para Professionals | No. | 2 | 2 | 100 | 0 | 0 | #DIV/0! | 2 | 2 | 100
2.1.6 | No. of days of Capacity Building of Community Resource persons | No. | 4 | 4 | 100 | 2 | 2 | 100 | 6 | 6 | 100
2.2 | Finances Leveraged- Breakup source wise (Rs. Lakhs): Please provide the break up in the manner mentioned below | [7 empty] | 0 | 0
2.2.1 | Credit leveraged from SHG Federations- Both Village Level and Cluster/Block Levels |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
2.2.2 | Credit leveraged from Banks |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
2.2.3 | Funds leveraged from other govt. programs (MGNREGA/RKVY etc) |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
[9 empty] | 0 | 0
2.4 | "Infrastructure & Marketing Fund" for MKSP Funding used as : (Rs. Lakh): Please provide the total fund here utilized and the break up of the funds as mentioned below |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
2.4.1 | capital investment for common infrastructure/CFC |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
2.4.2 | Capacity building of CRP |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
2.4.3 | Capacity building of Community Para Professionals |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
2.4.4 | Capacity building of target women farmers |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
[9 empty] | 0 | 0
2.5 | Physical Assets Created through leveraged funds (to be defined by PIA as provided in Profile): Please define the physical assets created and the value of investment against each of the assets | [7 empty] | 0 | 0
2.5.1 | Asset 1 |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
2.5.2 | Asset 2 |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
2.5.3 | Asset 3 |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
2.5.4 | Asset 4 |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
2.5.5 | Asset 5 |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
[5 empty] | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
[5 empty] | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3. Output | Please provide informations in the manner mentioned below, along with the relevant evidences in the annexure | [7 empty] | 0 | 0
3.1 | Incremental increase in crop output for the Women Farmers covered under MKSP | Qtls. |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.2 | Incremental increase in NTFP collection for Women Farmers covered under MKSP | Qtls. |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.3 | Incremental increase in revenue generation for Women Farmers covered by MKSP under sustainable agriculture | Rs. Lakhs |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.4 | Incremental increase in revenue generation for Women Farmers covered by MKSP under NTFP activities | Rs. Lakhs |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.5 | Incremental increase in revenue generation for Women Farmers covered by MKSP under Livestock activities | Rs. Lakhs |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.6 | Gross incremental revenue generation for the livelihood interventions in the area covered | Rs. Lakhs |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.7 | Gross incremental revenue generation from the Livelihood interventions per Women Farmer covered | Rs. Lakhs |  |  | #DIV/0! |  | 0 | #DIV/0! | 0 | 0 | #DIV/0!
3.8 | Benckmark productivity level Per acre | Qtls. |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.9 | No. of families meeting benchmark yield for crops grown under SA practices | No. |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
[9 empty] | 0 | 0
3.2 | Proportion of Families having Income Range from intervention sunder MKSP: Please provide information in the manner mentioned below | [7 empty] | 0 | 0
3.2.1 | < Rs.7500 |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.2.2 | Rs 7501-10000 |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.2.3 | Rs.10001-15000 |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.2.4 | more than Rs.15000 |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
[9 empty] | 0 | 0
3.3 | Average additional foodgrains per family | [7 empty] | 0 | 0
3.3.1 | Food Sufficiency | [7 empty] | 0 | 0
3.3.1.1 | less than 6 months |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.3.1.2 | 7-9 months |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.3.1.3 | 9-12 month |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.3.1.4 | > 12 months |  |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
[9 empty] | 0 | 0
3.4 | Social Capital Development | [7 empty] | 0 | 0
3.4.1 | Community Resources Persons (Women CRPs only) trained in Sustainable agriculture/NTFP/Livestock practices: Please provide the total no. here and the breakup under each subhead in the annexure | no. | 30 | 32 | 106.6667 | 30 | 39 | 130 | 60 | 71 | 118.3333
3.4.2 | Community Para Professionals: Please provide the informations in the manner mentioned below |  | 20 | 20 | 100 | 20 | 17 | 85 | 40 | 37 | 92.5
3.4.2.1 | Women |  | 6 | 8 | 133.3333 | 8 | 7 | 87.5 | 14 | 15 | 107.1429
3.4.2.2 | Men |  | 14 | 12 | 85.7143 | 12 | 10 | 83.3333 | 26 | 22 | 84.6154
[9 empty] | 0 | 0
3.5 | Marketing initiatives: Please provide the informations in the manner mentioned below and relevant evidence in the annexure | [7 empty] | 0 | 0
3.5.1 | Gross incremental revenue generation from all the crops/products marketed collectively | Rs. lakhs |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.5.2 | Gross Incremental benefit per Women members involved in collective marketing | Rs Lakhs |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.5.3 | Net returns to the Producer Organizations from Collective marketing | Rs Lakhs |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.5.4 | Net returns to the Producer Organizations from Value addition | Rs Lakhs |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.5.5 | No. of women/men involved in Value addition by the Producers' organizations/NTFP collectives/Livestock related collectives | No. |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.5.6 | Mandays/Womendays of work created as a result of value addition activity | No. of days |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
3.5.7 | Total amount of wages paid to the workers involved in Value addition activity | Rs Lakhs |  |  | #DIV/0! |  |  | #DIV/0! | 0 | 0 | #DIV/0!
| No. of Value chain studies completed | Nos.
Note on H11: Compaq: Do mention the date of reporting

## Summary Phy. quarterly
Sl. No. | Particulars | % achievement of target for the current quarter | % achievement of overall target
1 | Total No. of Mahila Kisan Covered | 98.7273 | 98.7273
2 | Total Agricultural area of Mahila Kisan in the area of operations (Net cropped area) | 123.049 | 123.049
4 | No. of Mahila Kisan trained in atleast one activity covered under MKSP | 60 | 70.5556
5 | Livelihood groups formed and working | 90.9091 | 95.7746
6 | No. of training modules developed for SHG members | 100 | 100
7 | No. of Training modules developed for Community Resource Persons | 100 | 100
8 | No. of days of Capacity building of women farmers | 40 | 66.6667
9 | No. of days of Capacity building of Community Para Professionals | #DIV/0! | 100
10 | No. of days of Capacity Building of Community Resource persons | 100 | 100
11 | Community Resources Persons (Women CRPs only) trained in Sustainable agriculture/NTFP/Livestock practices | 130 | 118.3333
12 | Incremental increase in crop output for the Women Farmers covered under MKSP | #DIV/0! | #DIV/0!
13 | Incremental increase in NTFP collection for Women Farmers covered under MKSP | #DIV/0! | #DIV/0!
14 | % of families meeting benchmark yield | #DIV/0! | #DIV/0!
Summary sheet: Physical Progress

## Quarterly fin. review-detail
QUARTERLY FINANCE REVIEW DETAIL For the Quarter April to June 2014
PIA - ORGANISATION FOR RURAL RECONSTRUCTION AND INTEGRATED SOCIAL SERVICE ACTIVITIES (ORRISSA)
Sl. No | Budget Heads | Total available funds- as per the budget approval for the given year | Total expenditure till the end of previous reporting quarter | Expenditure as % of total available funds- till the end of previous reporting period | Opening balance for the given reporting period | Expenditure in the current quarter | Expenditure as % of opening balance for the quarter | Balance unutilized funds at the end of reporting quarter | Unutilized funds as % of total available funds- approved for the year
100 | Project Inception | 550000 | 444370 | 80.7945 | 5630 | 0 |  | 105630 | 19.2055
101 | Mahila Kisan profiling | 150000 | 144370 | 96.2467 | 5630 | 0 |  | 5630 | 3.7533
102 | DPR Preparation | 200000 | 200000 | 100 | 0 | 0 |  | 0 | 0
103 | Technical protocols documentation | 100000 | 100000 | 100 | 0 | 0 |  | 0 | 0
104 | Value-chain Studies | 100000 | 0 | 0 | 0 | 0 |  | 100000 | 100
200 | Institution Building | 1821340 | 482875 | 26.5121 | 554125 | 237000 | 42.7701 | 1101465 | 60.4755
201 | Mobilisation & Promotion of producer groups | 531840 | 111875 | 21.0355 | 175625 | 0 |  | 419965 | 78.9645
202 | Promotion of producer group federation | 80000 | 0 | 0 | 40000 | 0 |  | 80000 | 100
203 | Management support to producer federation | 1209500 | 371000 | 30.6738 | 338500 | 237000 | 70.0148 | 601500 | 49.7313
300 | Capacity Building | 4265450 | 249958 | 5.8601 | 3041492 | 136180 | 4.4774 | 3879312 | 90.9473
301 | Training module development : Print | 780000 | 10000 | 1.2821 | 770000 | 90000 | 11.6883 | 680000 | 87.1795
302 | Training module development : audio-visual | 500000 | 0 | 0 | 0 | 0 |  | 500000 | 100
303 | Training equipment & material | 448000 | 0 | 0 | 224000 | 0 |  | 448000 | 100
304 | Training to CRP | 202000 | 93963 | 46.5163 | 108037 | 0 |  | 108037 | 53.4837
305 | Trainings to para-professionals | 62000 | 29605 | 47.75 | 32395 | 0 |  | 32395 | 52.25
306 | Training to Community | 1063950 | 81990 | 7.7062 | 731960 | 46180 | 6.3091 | 935780 | 87.9534
307 | Training to leaders & PRI | 112000 | 0 | 0 | 112000 | 0 |  | 112000 | 100
308 | Exposure visits of CRPs to immersion sites | 120000 | 0 | 0 | 120000 | 0 |  | 120000 | 100
309 | Exposure visit of para-professional to immersion sites | 40000 | 0 | 0 | 40000 | 0 |  | 40000 | 100
310 | Exposure visit of Community to immersion sites | 25000 | 0 | 0 | 25000 | 0 |  | 25000 | 100
311 | Service charge to CRP | 500000 | 0 | 0 | 500000 | 0 |  | 500000 | 100
312 | Service charge to para-professionals | 300000 | 34400 | 11.4667 | 265600 | 0 |  | 265600 | 88.5333
313 | Field level handholding capacity building support to the Producer Groups and Cooperatives by professional experience holders | 112500 | 0 | 0 | 112500 | 0 |  | 112500 | 100
400 | Community Investment Support | 520000 | 0 | 0 | 520000 | 0 |  | 520000 | 100
401 | Community Infrastructure | 0 | 0 |  | 0 | 0 |  | 0
402 | Inputs to the mahila kisan (grant/subsidy/full loan) | 450000 | 0 | 0 | 450000 | 0 |  | 450000 | 100
403 | Inputs to producer groups/ federation (grant/subsidy/full loan) | 70000 | 0 | 0 | 70000 | 0 |  | 70000 | 100
404 | Operational Fund of Producer federation | 0 | 0 |  | 0 | 0 |  | 0
500 | Knowledge Management | 309950 | 95000 | 30.6501 | 214950 | 33000 | 15.3524 | 181950 | 58.703
501 | Identification of best practices | 19890 | 0 | 0 | 19890 | 0 |  | 19890 | 100
502 | Documentation of best practices | 0 | 0 |  | 0 | 0 |  | 0
503 | Dissemination of best practices | 0 | 0 |  | 0 | 0 |  | 0
504 | Yearly Data management (MIS) | 150000 | 55000 | 36.6667 | 95000 | 33000 | 34.7368 | 62000 | 41.3333
505 | Dev and Management of Project Website | 100000 | 40000 | 40 | 60000 | 0 |  | 60000 | 60
506 | Village and Project Display Board | 40060 | 0 | 0 | 40060 | 0 |  | 40060 | 100
600 | Monitoring & Evaluation | 558000 | 205710 | 36.8656 | 247290 | 49157 | 19.8783 | 303133 | 54.3249
601 | Baseline survey | 300000 | 205710 | 68.57 | 53290 | 0 |  | 94290 | 31.43
602 | Endline survey | 0 | 0 |  | 0 | 0 |  | 0
603 | Independent evaluation studies | 0 | 0 |  | 0 | 0 |  | 0
604 | Public information disclosure | 84000 | 0 | 0 | 84000 | 0 |  | 84000 | 100
605 | Social Audit | 0 | 0 |  | 0 | 0 |  | 0
606 | Monitoring of programmes | 144000 | 0 | 0 | 80000 | 49157 | 61.4462 | 94843 | 65.8632
607 | Project Monitoring committee Meeting | 30000 | 0 | 0 | 30000 | 0 |  | 30000 | 100
700 | Administration Expenditure (Maximum 5% of total project cost) | 548600 | 160818 | 29.3143 | 207782 | 101864 | 49.0245 | 285918 | 52.1178
701 | Staff salaries | 384700 | 125000 | 32.4929 | 89700 | 96000 | 107.0234 | 163700 | 42.5526
702 | Travel & conveyance | 72000 | 28318 | 39.3306 | 43682 | 5130 | 11.744 | 38552 | 53.5444
703 | Stationary | 40800 | 0 | 0 | 40800 | 734 | 1.799 | 40066 | 98.201
704 | Communication | 33600 | 0 | 0 | 33600 | 0 |  | 33600 | 100
705 | Audit Expenses | 17500 | 7500 | 42.8571 | 0 | 0 |  | 10000 | 57.1429
| Grand Total | 8573340 | 1638731 | 19.1143 | 4791269 | 557201 | 11.6295 | 6377408 | 74.3865
Note on B3: Compaq: Please fill the heads which are relevant to you at a given point of time according to the timeline submitted by you as per proposal
Note on B5: Compaq: Please provide the total amount here
Note on B10: Compaq: Please provide the total amount here
Note on B14: Compaq: Please provide the total amount here
Note on B28: Compaq: Please provide the total amount here.
Note on B33: Compaq: Please provide the total amount
Note on B40: Compaq: Please give the total amount
Note on B48: Compaq: Please give the total amount

## deficit finance
Name of the PIA: Regd. No:
Project Name: Strengthening Adivasi Farm Women Self-Help Cooperative to enable them pure sustainable livelihoods in the Malkangiri & Kandhamal
Date of PAC:08.03.2013
Date of Fund release (Current tranche):25.10.2013
No. of tranches received:01
Total Sanctioned Amount till date:34,300,000.00
Total Project Period:25.10.2013 to 24.10.2016
Provisional Expenses Statement |  | From:01.04.2014 |  |  | To:30.06.2014
Sl.No | Budget Heads | Budget MKSP |  |  |  | Expenditure MKSP |  |  | Variance |  |  | Variance in % |  |  |  | Expenditure Non-MKSP (other ) |  |  | Expenditure Total (all sources) |  |  | % MKSP Funds
|  | Total Budget as per proposal | Up to Previous Reporting Period (A) | Current Period (B) | Up to end of reporting period (A+B)= C | Upto previous Reporting Period (D) | Current Period E | Up to end of reporting period (D+E)= F | Upto end of previous reporting period (A-D)= X | Upto current period (B-E)= G | Upto end of all reporting periods (C-F)= H | Upto the end of previous reporting period ((X/A)*100)= Y | Upto the end of current reporting period ((G/B)*100)=I | Upto the end of all reporting periods ((H/C)*100)=J |  | Upto the end of previous reporting period (K) | Current Period (L) | Up to end of all reporting period (M=K+L) | Upto the end of previous reporting period (N=K+D) | Current Period (O= E+L) | Up to end of all reporting period (P=N+O) | Upto the end of Previous reporting period ((D/N)*100)=Q | Current Period ((E/O)*100)=R | Up to end of reporting period ((F/P)*100)=S
100 | Project Inception | 550000 | 450000 | 100000 | 550000 | 444370 | 0 | 444370 | 5630 | 100000 | 105630 | 1.2511 | 100 | 19.2055 |  | 0 | 0 | 0 | 444370 | 0 | 444370 | 100 |  | 100
101 | Mahila Kisan profiling | 150000 | 150000 | 0 | 150000 | 144370 | 0 | 144370 | 5630 | 0 | 5630 | 3.7533 |  | 3.7533 |  | 0 | 0 | 0 | 144370 | 0 | 144370 | 100 |  | 100
102 | DPR Preparation | 200000 | 200000 | 0 | 200000 | 200000 | 0 | 200000 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 200000 | 0 | 200000 | 100 |  | 100
103 | Technical protocols documentation | 100000 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 100000 | 0 | 100000 | 100 |  | 100
104 | Value-chain Studies | 100000 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 100000 | 100000 |  | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
200 | Institution Building | 5590070 | 1037000 | 784340 | 1821340 | 482875 | 237000 | 719875 | 554125 | 547340 | 1101465 | 53.4354 | 69.7835 | 60.4755 |  | 0 | 0 | 0 | 482875 | 237000 | 719875 | 100 | 100 | 100
201 | Mobilisation & Promotion of producer groups | 1293750 | 287500 | 244340 | 531840 | 111875 | 0 | 111875 | 175625 | 244340 | 419965 | 61.087 | 100 | 78.9645 |  | 0 | 0 | 0 | 111875 | 0 | 111875 | 100 |  | 100
202 | Promotion of producer group federation | 404000 | 40000 | 40000 | 80000 | 0 |  | 0 | 40000 | 40000 | 80000 | 100 | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
203 | Management support to producer federation | 3892320 | 709500 | 500000 | 1209500 | 371000 | 237000 | 608000 | 338500 | 263000 | 601500 | 47.7097 | 52.6 | 49.7313 |  | 0 | 0 | 0 | 371000 | 237000 | 608000 | 100 | 100 | 100
300 | Capacity Building | 12013120 | 3291450 | 974000 | 4265450 | 249958 | 136180 | 386138 | 3041492 | 837820 | 3879312 | 92.4058 | 86.0185 | 90.9473 |  | 0 | 0 | 0 | 249958 | 136180 | 386138 | 100 | 100 | 100
301 | Training module development : Print | 780000 | 780000 | 0 | 780000 | 10000 | 90000 | 100000 | 770000 | -90000 | 680000 | 98.7179 |  | 87.1795 |  | 0 | 0 | 0 | 10000 | 90000 | 100000 | 100 | 100 | 100
302 | Training module development : audio-visual | 600000 | 0 | 500000 | 500000 | 0 |  | 0 | 0 | 500000 | 500000 |  | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
303 | Training equipment & material | 448000 | 224000 | 224000 | 448000 | 0 |  | 0 | 224000 | 224000 | 448000 | 100 | 100 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
304 | Training to CRP | 505000 | 202000 | 0 | 202000 | 93963 |  | 93963 | 108037 | 0 | 108037 | 53.4837 |  | 53.4837 |  | 0 | 0 | 0 | 93963 | 0 | 93963 | 100 |  | 100
305 | Trainings to para-professionals | 186000 | 62000 | 0 | 62000 | 29605 |  | 29605 | 32395 | 0 | 32395 | 52.25 |  | 52.25 |  | 0 | 0 | 0 | 29605 | 0 | 29605 | 100 |  | 100
306 | Training to Community | 3528000 | 813950 | 250000 | 1063950 | 81990 | 46180 | 128170 | 731960 | 203820 | 935780 | 89.9269 | 81.528 | 87.9534 |  | 0 | 0 | 0 | 81990 | 46180 | 128170 | 100 | 100 | 100
307 | Training to leaders & PRI | 336000 | 112000 | 0 | 112000 | 0 |  | 0 | 112000 | 0 | 112000 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
308 | Exposure visits of CRPs to immersion sites | 360000 | 120000 | 0 | 120000 | 0 |  | 0 | 120000 | 0 | 120000 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
309 | Exposure visit of para-professional to immersion sites | 120000 | 40000 | 0 | 40000 | 0 |  | 0 | 40000 | 0 | 40000 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
310 | Exposure visit of Community to immersion sites | 500000 | 25000 | 0 | 25000 | 0 |  | 0 | 25000 | 0 | 25000 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
311 | Service charge to CRP | 2723760 | 500000 | 0 | 500000 | 0 |  | 0 | 500000 | 0 | 500000 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
312 | Service charge to para-professionals | 1588860 | 300000 | 0 | 300000 | 34400 | 0 | 34400 | 265600 | 0 | 265600 | 88.5333 |  | 88.5333 |  | 0 | 0 | 0 | 34400 | 0 | 34400 | 100 |  | 100
313 | Field level handholding capacity building support to the Producer Groups and Cooperatives by professional experience holders | 337500 | 112500 | 0 | 112500 | 0 |  | 0 | 112500 | 0 | 112500 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
400 | Community Investment Support | 10643000 | 520000 | 0 | 520000 | 0 | 0 | 0 | 520000 | 0 | 520000 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
401 | Community Infrastructure | 4506000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
402 | Inputs to the mahila kisan (grant/subsidy/full loan) | 900000 | 450000 | 0 | 450000 | 0 |  | 0 | 450000 | 0 | 450000 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
403 | Inputs to producer groups/ federation (grant/subsidy/full loan) | 2297000 | 70000 | 0 | 70000 | 0 |  | 0 | 70000 | 0 | 70000 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
404 | Operational Fund of Producer federation | 2940000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
500 | Knowledge Management | 1685580 | 309950 | 0 | 309950 | 95000 | 33000 | 128000 | 214950 | -33000 | 181950 | 69.3499 |  | 58.703 |  | 0 | 0 | 0 | 95000 | 33000 | 128000 | 100 | 100 | 100
501 | Identification of best practices | 300000 | 19890 | 0 | 19890 | 0 |  | 0 | 19890 | 0 | 19890 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
502 | Documentation of best practices | 450000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
503 | Dissemination of best practices | 280000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
504 | Yearly Data management (MIS) | 450000 | 150000 | 0 | 150000 | 55000 | 33000 | 88000 | 95000 | -33000 | 62000 | 63.3333 |  | 41.3333 |  | 0 | 0 |  | 55000 | 33000 | 88000 | 100 | 100 | 100
505 | Dev and Management of Project Website | 159520 | 100000 | 0 | 100000 | 40000 | 0 | 40000 | 60000 | 0 | 60000 | 60 |  | 60 |  | 0 | 0 |  | 40000 | 0 | 40000 | 100 |  | 100
506 | Village and Project Display Board | 46060 | 40060 | 0 | 40060 | 0 |  | 0 | 40060 | 0 | 40060 | 100 |  | 100 |  | 0 | 0 |  | 0 | 0 | 0
600 | Monitoring & Evaluation | 2104000 | 453000 | 105000 | 558000 | 205710 | 49157 | 254867 | 247290 | 55843 | 303133 | 54.5894 | 53.1838 | 54.3249 |  | 0 | 0 | 0 | 205710 | 49157 | 254867 | 100 | 100 | 100
601 | Baseline survey | 300000 | 259000 | 41000 | 300000 | 205710 | 0 | 205710 | 53290 | 41000 | 94290 | 20.5753 | 100 | 31.43 |  | 0 | 0 | 0 | 205710 | 0 | 205710 | 100 |  | 100
602 | Endline survey | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
603 | Independent evaluation studies | 525000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
604 | Public information disclosure | 252000 | 84000 | 0 | 84000 | 0 | 0 | 0 | 84000 | 0 | 84000 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
605 | Social Audit | 280000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
606 | Monitoring of programmes | 432000 | 80000 | 64000 | 144000 | 0 | 49157 | 49157 | 80000 | 14843 | 94843 | 100 | 23.1922 | 65.8632 |  | 0 | 0 | 0 | 0 | 49157 | 49157 |  | 100 | 100
607 | Project Monitoring committee Meeting | 90000 | 30000 | 0 | 30000 | 0 |  | 0 | 30000 | 0 | 30000 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
700 | Administration Expenditure | 1714230 | 368600 | 180000 | 548600 | 160818 | 101864 | 262682 | 207782 | 78136 | 285918 | 56.3706 | 43.4089 | 52.1178 |  | 0 | 0 | 0 | 160818 | 101864 | 262682 | 100 | 100 | 100
701 | Staff salaries | 1210560 | 214700 | 170000 | 384700 | 125000 | 96000 | 221000 | 89700 | 74000 | 163700 | 41.7792 | 43.5294 | 42.5526 |  | 0 | 0 | 0 | 125000 | 96000 | 221000 | 100 | 100 | 100
702 | Travel & conveyance | 226980 | 72000 | 0 | 72000 | 28318 | 5130 | 33448 | 43682 | -5130 | 38552 | 60.6694 |  | 53.5444 |  | 0 | 0 | 0 | 28318 | 5130 | 33448 | 100 | 100 | 100
703 | Stationary | 128622 | 40800 | 0 | 40800 | 0 | 734 | 734 | 40800 | -734 | 40066 | 100 |  | 98.201 |  | 0 | 0 | 0 | 0 | 734 | 734 |  | 100 | 100
704 | Communication | 103068 | 33600 | 0 | 33600 | 0 | 0 | 0 | 33600 | 0 | 33600 | 100 |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0
705 | Audit Expenses | 45000 | 7500 | 10000 | 17500 | 7500 |  | 7500 | 0 | 10000 | 10000 | 0 | 100 | 57.1429 |  | 0 | 0 | 0 | 7500 | 0 | 7500 | 100 |  | 100
| Grand Total | 34300000 | 6430000 | 2143340 | 8573340 | 1638731 | 557201 | 2195932 | 4791269 | 1586139 | 6377408 | 74.5143 | 74.0031 | 74.3865 | 0 | 0 | 0 | 0 | 1638731 | 557201 | 2195932 | 100 | 100 | 100
| MKSP Fund Balance for the current reporting period | Amount (Rs.)
| Opening Balance as on first day of current reporting period | 4791269
| Add: Grant Received during the current reporting period | 2143340
| Add: Bank Interest Received | 101375
| Less: Expenditure during the Current Period | 557201
| Balance as on end of reporting period | 6478783
| Bank Interest on MKSP Funds | Amount (Rs.)
| Bank Interest Received up to Previous Reporting Period | 0
| Bank Interest Received Current Reporting Period | 101375
| Total | 101375
Note on B10: Compaq: Please fill the heads which are relevant to you at a given point of time according to the timeline submitted by you as per proposal
Note on B12: Compaq: Please provide the total amount here
Note on B17: Compaq: Please provide the total amount here
Note on B21: Compaq: Please provide the total amount here
Note on B35: Compaq: Please provide the total amount here.
Note on B40: Compaq: Please provide the total amount
Note on B47: Compaq: Please give the total amount
Note on B55: Compaq: Please give the total amount

## Summary quarterly financial
Financial Progress: Summary
Outreach Details
Basic Details | Progress till the previous reporting quarter | Progress in the current quarter
Total No. of women farmers covered under MKSP :
Balance unutilized funds
Sources of Funds | Unutilized funds | Unutilized funds as % of total available funds for quarter
MKSP | 6377408 | 74.3865
Other (Please specify. In case of more than one source, mention them seperately by addition of rows) | 0
Total | 6377408 | 74.3865
Componentwise break up of the expenditure for the quarter
Broad cost heads for MKSP | Expenditure | Expenditure as % of opening balance for the quarter
Project Inception | 0 | 0
Institution Building | 237000 | 42.7701
Capacity Building | 136180 | 4.4774
Community Investment Support | 0 | 0
Knowledge Management | 33000 | 15.3524
Monitoring & Evaluation | 49157 | 19.8783
Administration | 101864 | 49.0245
Cash Inflows
Particulars | MKSP | Other (Please specify. In case of more than one source, mention them seperately by addition of columns) | Total
Opening Balance | 4791269 | 0 | 4791269
Receipts | 2143340 | 0 | 2143340
Total amount for the quarter | 6934609 | 0 | 6934609
Cash Outflows
Particulars | Amount | Expenditure as % of total available funds
MKSP | 557201 | 8.0351
Other (Please specify. In case of more than one source, mention them seperately by addition of rows) | 0
Total | 557201 | 8.0351

## Summary sheet PIA
Input Indicators
Name of PIA | No of Districts | No. of blocks entered | No. of villages entered | No of Mahila Kisans | No of Mahila Kisans in SHGs | No. of producer groups formed | No of Mahila Kisans in Producers' groups | No. of trainings of Mahila Kisans held | No of days of training given to Mahila Kisan | No. of Mahila Kisans trained | No. of CRPs selected | No. of CRPs trained | No of trainings held for CRP | No of training days for CRP | No. of Training modules developed and conducted | Area of Land under SA (acres) |  | No. of families adopting SA practices | A/V training modules developed for community/CRP training
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[16 empty] | Khariff | Rabi
Organisation for Rural Reconstruction & Integrated Social Service Activities (ORRISSA) | 2 | 2 | 66 | 3012 | 1905 | 68 | 2812 | 6 | 12 | 127 | 60 | 60 | 2 | 4 | 4 | 2518 |  | 2174 | 5
Best practices identified
Sl. No. | Particulars | Area of activity under MKSP | No. of Mahila Kisan covered under the practice | Benefits accrued to the Mahila Kisan as a result of the practice (in Lakhs) | Remarks
Note on A9: Compaq: Please add rows in case of requirement
Note on E10: Compaq: Applicable only in case of the activities which can have quantifiable outputs. Mention only in case it is applicable